## Sheet1
MIlestone | Tasks | Assigned To | Date
0 - Planning
0.1 | Component Research | Everyone
0.2 | Magic Mirror Research | Alan Palayil
0.3 | Alexa API and Google Assitant Research | Alan Palayil
0.4 | OpenCV Research | Gabriel Gutierrez & Fabian Garcia
0.5 | Gesture Recognition Research | Gabriel Gutierrez & Fabian Garcia
1 - Design - 01
1.1 | Design Schematic | Everyone
1.2 | Acquire Required Parts | Everyone | 2022-03-01
1.3 | Test Parts and Ensure Functionality | Everyone | 2022-03-01
1.4 | Alexa API and Google Assistant Implementation | Alan Palayil | 2022-03-10
1.5 | OpenCV Setup | Fabian Garcia & Gabriel Gutierrez | 2022-03-10
1.6 | Magic Mirror Screen Setup | Alan Palayil | 2022-03-12
1.7 | Gesture Control Hand Mapping | Fabian Garcia | 2022-03-14
1.8 | Record Specific Gestures | Gabriel Gutierrez | 2022-03-21
1.9 | Gesture Implementation | Gabriel Gutierrez | 2022-03-21
1.1 | Speaker and Camera Connection | Everyone | 2022-03-28
1 - Design - 02
1.1 | Implement android OS | Alan | 2022-04-01
1.2 | Test widgets | Fabian | 2022-04-01
1.3 | Look into security apps | Gabriel | 2022-04-01
1.4 | Compile Everything | Everyone | 2022-03-12
2 - Completeion
2.1 | Create frame | Alan Palayil | 2022-04-15
2.2 | Assemble Components | Everyone | 2022-04-25